Cross-Dataset Testing — Design (Arabic focus)

Arabic audio deepfake detection: generalization across XMAD-Bench, AFAD-MSA, and dialectal data

Paper-02 Reproducibility · Prepared July 2026 · supersedes the English-focused draft for the primary plan

# 1. Objective and rationale

The focus of this study is Arabic audio deepfake detection. Reproducing XMAD-Bench on its own Arabic data confirms the authors' in-dataset claims but, by construction, tends to yield positive results. The real test is whether an Arabic-trained detector still works on a DIFFERENT Arabic corpus with different speakers, sources, and generative methods. This directly connects Paper-02 (XMAD-Bench) with the AFAD-MSA work, and targets the supervisor's point that Arabic — and especially Arabic DIALECTS — are a major, under-tested weak spot in voice security.

Research question. How much of an Arabic deepfake detector's performance survives a full change of Arabic corpus (XMAD-Arabic <-> AFAD-MSA), and how far does it degrade further on dialectal Arabic?

# 2. Datasets in scope (Arabic-centric)

| Dataset | Nature (Arabic) | Role |
| --- | --- | --- |
| XMAD-Bench (ar) | Real: CommonVoice-ar (in-domain) + MASC YouTube (cross-domain). Fakes: fairseq+KNN-VC/FreeVC and XTTSv2. | Primary corpus A. Reproduce first, then cross-test. |
| AFAD-MSA | Arabic MSA. HF elsayedissa/AFAD-MSA; code github.com/elsayed-issa/arabic-audio-deepfake-detection. 4 out-of-domain TTS test sets: xtts, fishaudio, mms, speecht5. Native detectors AASIST/RawNet2. | Primary corpus B (cross-dataset partner). |
| ArFake | Arabic fake-audio set (harder to access). | Extension corpus C (if obtainable). |
| Dialectal Arabic | MASC (dialectal, real; already XMAD's ar cross-domain source); ADI/MGB dialect corpora (real). Dialectal FAKES are scarce. | Dialect stress test (Phase 3) — a genuine data gap = contribution. |
| ASVspoof (English) | English only. | Optional cross-LINGUAL anchor only; not the focus. |

# 3. Experimental design

## 3.1 Directions (core)

- A -> B: train on XMAD-Arabic, test on AFAD-MSA.

- B -> A: train on AFAD-MSA, test on XMAD-Arabic.

- Ceilings: in-dataset A->A (from the XMAD-Arabic reproduction) and B->B (from the AFAD-MSA reproduction). The GAP is the headline result.

- Extra targets: AFAD-MSA's four out-of-domain TTS sets (xtts, fishaudio, mms, speecht5) as additional test-only conditions — a per-generator generalization curve.

## 3.2 Hold the detector constant (key design choice)

The two papers use DIFFERENT detectors (XMAD: ResNet-18/50, AST, wav2vec2, SepTr; AFAD-MSA: AASIST, RawNet2). A clean cross-dataset comparison must fix ONE detector and vary only the data. Plan: reuse the (already-fixed) XMAD detectors — ResNet-18 and wav2vec2 first — trained and tested on BOTH corpora by reformatting AFAD-MSA into the XMAD pipeline. Optionally, a secondary cross-check trains AASIST on both. Never compare 'XMAD's model on XMAD data' vs 'AFAD's model on AFAD data' — that confounds model and data.

## 3.3 Metrics

Primary EER and AUC (threshold-independent; a fixed-threshold accuracy is misleading cross-dataset). Secondary accuracy for comparability with both papers (both report ACC/EER). Report the in-dataset -> cross-dataset delta per metric, per detector.

## 3.4 Experiment matrix (Phase 1)

| Train \ Test | XMAD-Ar (test) | AFAD-MSA (test) |
| --- | --- | --- |
| XMAD-Ar | A->A (ceiling) | A->B (cross) |
| AFAD-MSA | B->A (cross) | B->B (ceiling) |

Each cell x detector x 3 runs (mean +/- SD).

# 4. Data harmonization and preprocessing (confound control)

Both corpora MUST pass through identical preprocessing so differences reflect genuine domain shift, not pipeline mismatch. Reuse the XMAD pipeline for both.

- 16 kHz mono; XMAD's fixed 5 s crop/pad applied to AFAD too.

- Silence trimming (critical): trim identically for both; leading-silence length is a known shortcut in anti-spoofing data. XMAD already trims; apply the same to AFAD.

- Loudness normalization identical for both; identical front-end (spectrogram / model extractor).

- Arabic-specific: XMAD-ar (CommonVoice) and AFAD-MSA are both broadly MSA; MASC/ADI add dialects in Phase 3. Note the variety (MSA vs dialect) explicitly so it is not silently confounded.

# 5. Label harmonization

Map both corpora to is_fake in {0 (real/bonafide), 1 (fake)}. For AFAD-MSA, keep the generating TTS system (xtts / fishaudio / mms / speecht5) as metadata (like an attack id) for per-generator analysis. Positive class = fake, consistently.

# 6. Implementation approach

Reuse the already-fixed XMAD detection code by wrapping AFAD-MSA into the same on-disk layout, so training/eval and preprocessing are identical to XMAD.

afad-msa/
  real/   *.wav         # bonafide Arabic MSA
  fake/   *.wav         # synthesized
  meta.csv              # sample_name, is_fake, split, tts_system

A converter (afad_to_xmad.py) reads the AFAD-MSA HuggingFace splits / repo manifests, writes meta.csv, and points to the audio files. Then: B->A trains on this folder with XMAD-Arabic as test; A->B loads the XMAD-Arabic checkpoint and evaluates here. Verify counts against the AFAD paper's split sizes before running.

# 7. Evaluation protocol

- 3 runs per cell per detector; mean +/- SD (no fixed seed, as in the reproduction).

- Always report the in-dataset ceiling beside the cross-dataset result; the delta is the finding.

- Per-generator breakdown on AFAD (xtts/fishaudio/mms/speecht5) and per-source on XMAD (CommonVoice vs MASC).

- Real-vs-real probe: classify the two corpora's REAL Arabic audio; if trivially separable, part of the drop is a real-source gap, not fake-detection failure.

# 8. Hypotheses / expected outcomes

- Large cross-dataset degradation both directions (EER rising well above in-dataset), consistent with XMAD's own in->cross drop and the anti-spoofing literature.

- wav2vec2 (self-supervised) generalizes better across Arabic corpora than plain ResNet CNNs.

- The more diverse training corpus (XMAD-ar: multi-generator + CommonVoice+MASC) transfers to AFAD better than AFAD -> XMAD.

- Dialectal Arabic (Phase 3) is the hardest condition and the biggest performance cliff — the core security concern.

# 9. Threats to validity

- Silence/preprocessing shortcuts — top threat; mitigated by identical trimming and front-end.

- Real-source gap (CommonVoice vs AFAD source vs MASC YouTube) may masquerade as generalization loss — hence the real-vs-real probe.

- MSA-vs-dialect confound — keep variety explicit; do not mix silently.

- Detector-family difference between the two papers — controlled by holding ONE detector constant (Section 3.2).

- Label/split conversion errors — validate against AFAD's published split sizes.

# 10. Phased plan

| Phase | Scope | Output |
| --- | --- | --- |
| 0 | Reproduce XMAD-Arabic (in + cross-domain) — anchor A->A | Arabic reproduction row in the tracker |
| 1 | XMAD-Ar <-> AFAD-MSA, ResNet-18 + wav2vec2, both directions, 3 runs, confound controls | First Arabic cross-dataset matrix |
| 2 | Add AFAD OOD TTS sets as test targets; add AST/SepTr; optional AASIST cross-check | Per-generator + detector ranking |
| 3 | Dialectal Arabic: MASC/ADI + ArFake; generate dialectal fakes where none exist | Dialect stress test — key contribution |

Compute: Phase 0 (XMAD Arabic) is ~5x German, best on the GPU server. AFAD-MSA is smaller. Test-only directions (A->B with an existing checkpoint) are nearly free.

# 11. Data access and licensing

- XMAD-Bench (ar): already downloaded; CC BY-NC-SA 4.0 + EULA.

- AFAD-MSA: HuggingFace elsayedissa/AFAD-MSA and github.com/elsayed-issa/arabic-audio-deepfake-detection — confirm the licence/redistribution terms.

- ArFake: access to be arranged (noted as harder).

- MASC / ADI dialect corpora: check individual licences; MASC is real-only (dialectal fakes must be generated).

# 12. Open questions for supervisor

- Confirm Phase-1 detector set (ResNet-18 + wav2vec2 first) and the hold-detector-constant approach.

- Priority of AFAD OOD TTS sets vs. moving straight to dialect (Phase 3).

- For dialects: obtain ArFake, or generate dialectal deepfakes from MASC/ADI real speech? (latter is a contribution but more work).

- Whether to add a secondary AASIST cross-check to bridge to the AFAD-MSA paper's own detector.